Asphalt Price Adjustment

Asphalt price adjustment for asphalt binder will be determined on a monthly basis by the following formula:

A  =  (MA - BA) x T

where:	A	=	Asphalt Price Adjustment

MA	=	Monthly Asphalt Price Index

BA	=	Basic Asphalt Price Index

T	=	Tons of New Asphalt Binder (see Note)

Note:	The weight of asphalt binder eligible for price adjustment will be determined by multiplying the percentage of new asphalt binder in the approved job mix formula by the weight of HMA.

Asphalt price adjustment for tack coat and prime coat will be determined on a monthly basis by the following formula:

A  =  (B) x (I) x (C) x (M) x (G)

where:	A	=	Asphalt Price Adjustment

B	=	Bid Price for Tack Coat/Prime Coat

I	=	Asphalt Price Adjustment Factor (see Note)

C	=	Petroleum Content of the Tack Coat and Prime Coat in Percent by Volume:

Use 100% for cutbacks

90% for inverted emulsions

60% for RS or similar type emulsions

M	=	Percentage of Bid Price Applicable to Materials 	Only: Use 82%

G 	=	Gallons of Tack Coat and Prime Coat Furnished and Applied

Note:	Asphalt price adjustment factor for a given month will be a percentage increase or decrease determined by comparing that month’s monthly asphalt price index with the basic asphalt price index.

The monthly asphalt price index will be the average of quotations from suppliers serving the area in which the Project is located, and will be determined by the Department each month.  For that part of the State north of and including Route 195, the asphalt price index will be based on quotations from Chevron, Citgo, and, Valero Refining Company New Jersey.  For that part of the State south of Route 195, the index will be based on quotations from Coastal, Chevron, Citgo, and Valero Refining Company New Jersey.

The basic asphalt price index will be the most recent monthly asphalt price index before receipt of bids.

Should a monthly asphalt price index increase 50 percent or more over the basic asphalt price index, no additional HMA shall be furnished for the Project without written approval from the Director of Construction Services and Materials.

Should a monthly asphalt price index decrease from the basic asphalt price index, payments will be decreased accordingly.

Asphalt price adjustment for work performed after the time of completion, will be based on the asphalt price index for the month in which the work was to be completed, except if the monthly asphalt price index decreases after the completion date, the asphalt price adjustment will be decreased accordingly.

Asphalt price adjustment will be on a lump sum basis, and an estimated amount to cover the asphalt price adjustment will be included in the Proposal.  Payments for increases will be made from this amount.

Asphalt price adjustments will not be made in those months for which the monthly asphalt price index has changed by less than five percent from the basic asphalt price index.

Basis of Payment.

Payment will be made under:

Pay Item	Pay Unit

ASPHALT PRICE ADJUSTMENT	LUMP SUM